## Daily tracker
Raised |  | Date | Opening balance | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | Week total | Cumulative | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | Week total | Cumulative | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | Week total | Cumulative | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | Week total | Cumulative | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | Week total | Cumulative | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | Week total | Cumulative | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | Week total | Cumulative | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | Week total | Cumulative | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | Week total | Cumulative | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | Week total | Cumulative | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | Week total | Cumulative | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | Week total | Cumulative | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | Week total | Cumulative | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | Week total | Cumulative | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | Week total | Cumulative | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | Week total | Cumulative
|  | Critical | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0
|  | Serious | 5 | [5 empty] | 0 | 5 |  |  |  | 1 |  | 1 | 6 | 1 | 1 |  |  |  | 2 | 8 | [5 empty] | 0 | 8 |  | 1 |  |  |  | 1 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9 | [5 empty] | 0 | 9
|  | High | 28 |  | 1 | 1 | 1 | 1 | 4 | 32 |  | 1 |  |  | 2 | 3 | 35 | 2 |  |  | 1 |  | 3 | 38 | 4 |  | 1 |  |  | 5 | 43 | 1 | 1 |  |  |  | 2 | 45 |  |  |  |  | 1 | 1 | 46 |  | 1 |  |  |  | 1 | 47 | [5 empty] | 0 | 47 |  | 1 |  |  |  | 1 | 48 | 1 |  |  |  | 1 | 2 | 50 | [5 empty] | 0 | 50 |  |  |  |  | 1 | 1 | 51 |  |  | 1 |  |  | 1 | 52 | [5 empty] | 0 | 52 | [5 empty] | 0 | 52 | [5 empty] | 0 | 52
|  | Medium | 15 | 1 | 1 | 2 |  | 2 | 6 | 21 |  |  |  | 2 | 1 | 3 | 24 | 2 |  | 1 | 1 | 1 | 5 | 29 | 2 | 2 | 4 |  |  | 8 | 37 | 2 |  |  |  |  | 2 | 39 | [5 empty] | 0 | 39 |  | 1 | 1 |  |  | 2 | 41 |  |  |  | 1 | 2 | 3 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44
|  | Low | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20
|  | Very Low | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20
|  | Total | 88 | 1 | 2 | 3 | 1 | 3 | 10 | 98 | 0 | 1 | 0 | 3 | 3 | 7 | 105 | 5 | 1 | 1 | 2 | 1 | 10 | 115 | 6 | 2 | 5 | 0 | 0 | 13 | 128 | 3 | 2 | 0 | 0 | 0 | 5 | 133 | 0 | 0 | 0 | 0 | 1 | 1 | 134 | 0 | 2 | 1 | 0 | 0 | 3 | 137 | 0 | 0 | 0 | 1 | 2 | 3 | 140 | 0 | 1 | 0 | 0 | 0 | 1 | 141 | 1 | 0 | 0 | 0 | 1 | 2 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 1 | 1 | 144 | 0 | 0 | 1 | 0 | 0 | 1 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 145
Resolved |  | Date | Opening balance | 2020-01-13 | 2020-01-14 | 2020-01-15 | 2020-01-16 | 2020-01-17 | Week total | Cumulative | 2020-01-20 | 2020-01-21 | 2020-01-22 | 2020-01-23 | 2020-01-24 | Week total | Cumulative | 2020-01-27 | 2020-01-28 | 2020-01-29 | 2020-01-30 | 2020-01-31 | Week total | Cumulative | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07 | Week total | Cumulative | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-02-14 | Week total | Cumulative | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | Week total | Cumulative | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28 | Week total | Cumulative | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | Week total | Cumulative | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13 | Week total | Cumulative | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | Week total | Cumulative | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | Week total | Cumulative | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | Week total | Cumulative | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | Week total | Cumulative | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | Week total | Cumulative | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | Week total | Cumulative | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | Week total | Cumulative
|  | Critical | [6 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0 | [5 empty] | 0 | 0
|  | Serious | 4 | [5 empty] | 0 | 4 |  |  |  |  | 1 | 1 | 5 |  |  | 1 |  | 1 | 2 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7 | [5 empty] | 0 | 7
|  | High | 11 |  | 2 | 1 | 1 |  | 4 | 15 |  | 1 | 3 | 3 | 3 | 10 | 25 | 1 |  | 1 | 1 |  | 3 | 28 |  | 1 | 2 | 1 |  | 4 | 32 |  | 1 |  |  | 2 | 3 | 35 |  |  |  |  | 1 | 1 | 36 |  |  | 1 |  |  | 1 | 37 | 2 |  |  | 1 |  | 3 | 40 |  | 2 |  |  |  | 2 | 42 |  |  |  |  | 1 | 1 | 43 | [5 empty] | 0 | 43 | [5 empty] | 0 | 43 |  |  | 1 |  |  | 1 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44 | [5 empty] | 0 | 44
|  | Medium | 11 |  |  |  |  | 1 | 1 | 12 | [5 empty] | 0 | 12 | 2 |  |  | 2 |  | 4 | 16 | 2 | 1 | 1 | 1 |  | 5 | 21 |  | 1 |  |  | 2 | 3 | 24 | 1 | 1 | 1 |  | 1 | 4 | 28 | 1 |  | 1 |  |  | 2 | 30 | 1 |  |  | 1 |  | 2 | 32 | 1 |  |  |  | 1 | 2 | 34 | 2 |  |  |  |  | 2 | 36 |  |  |  | 1 |  | 1 | 37 |  |  |  |  | 2 | 2 | 39 |  |  |  | 2 |  | 2 | 41 | [5 empty] | 0 | 41 | [5 empty] | 0 | 41 | [5 empty] | 0 | 41
|  | Low | 19 | [5 empty] | 0 | 19 |  |  | 1 |  |  | 1 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20 | [5 empty] | 0 | 20
|  | Very Low | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 | [5 empty] | 0 | 17 |  |  |  | 1 |  | 1 | 18 | [5 empty] | 0 | 18 | [5 empty] | 0 | 18 | [5 empty] | 0 | 18
|  | Total | 62 | 0 | 2 | 1 | 1 | 1 | 5 | 67 | 0 | 1 | 4 | 3 | 4 | 12 | 79 | 3 | 0 | 2 | 3 | 1 | 9 | 88 | 2 | 2 | 3 | 2 | 0 | 9 | 97 | 0 | 2 | 0 | 0 | 4 | 6 | 103 | 1 | 1 | 1 | 0 | 2 | 5 | 108 | 1 | 0 | 2 | 0 | 0 | 3 | 111 | 3 | 0 | 0 | 2 | 0 | 5 | 116 | 1 | 2 | 0 | 0 | 1 | 4 | 120 | 2 | 0 | 0 | 0 | 1 | 3 | 123 | 0 | 0 | 0 | 1 | 0 | 1 | 124 | 0 | 0 | 0 | 0 | 2 | 2 | 126 | 0 | 0 | 1 | 3 | 0 | 4 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 130
| Balance |  | 26 | 27 | 27 | 29 | 29 | 31 |  |  | 31 | 31 | 27 | 27 | 26 |  |  | 28 | 29 | 28 | 27 | 27 |  |  | 31 | 31 | 33 | 31 | 31 |  |  | 34 | 34 | 34 | 34 | 30 |  |  | 29 | 28 | 27 | 27 | 26 |  |  | 25 | 27 | 26 | 26 | 26 |  |  | 23 | 23 | 23 | 22 | 24 |  |  | 23 | 22 | 22 | 22 | 21 |  |  | 20 | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 19 | 19 |  |  | 19 | 19 | 19 | 19 | 18 |  |  | 18 | 18 | 18 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15 |  |  | 15 | 15 | 15 | 15 | 15

## Burndown
All Issues
| 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24thApr | 1st May
Actual Total Issues Raised | 88 | 98 | 105 | 115 | 128 | 133 | 134 | 137 | 140 | 141 | 143 | 143 | 144 | 145 | 145 | 145 | 145 | * update with actual each week
Actual Total Issues Resolved | 62 | 67 | 79 | 88 | 97 | 103 | 108 | 111 | 116 | 120 | 123 | 124 | 126 | 130 | 130 | 130 | 130 | * update with actual each week
Forecast Total Issues Raised | 88 | 98 | 105 | 115 | 128 | 133 | 134 | 137 | 140 | 141 | 143 | 143 | 144 | 145 | 147 | 149 | 151 | *Need to extrapolate from the last couple of weeks the forecast increase in issues raised per week and plot this
Target Total Issues Resolved | 62 | 67 | 79 | 88 | 97 | 103 | 108 | 111 | 116 | 120 | 123 | 124 | 126 | 130 | 134 | 138 | 142
Assuming 4 per week productivity
Critical / Serious / Highs Only
| 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24thApr | 1st May | AS ABOVE BUT ONLY FOR THE TOP 3 SEVERITIES
Actual Total Issues Raised | 33 | 37 | 41 | 46 | 51 | 54 | 55 | 56 | 56 | 57 | 59 | 59 | 60 | 61 | 61 | 61 | 61
Actual Total Issues Resolved | 15 | 19 | 30 | 35 | 39 | 42 | 43 | 44 | 47 | 49 | 50 | 50 | 50 | 51 | 51 | 51 | 51
Forecast Total Issues Raised | 33 | 37 | 41 | 46 | 51 | 54 | 55 | 56 | 56 | 57 | 59 | 59 | 60 | 61 | 61 | 61 | 61 | Assume no serious/high issue will be raised each week
Target Total Issues Resolved | 15 | 19 | 30 | 35 | 39 | 42 | 43 | 44 | 47 | 49 | 50 | 50 | 50 | 51 | 53 | 55 | 57 | Assume 2 serious/high issue will be resolved each week
Total Issues Raised By Severity | 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24thApr | 1st May | * update each week so we can the trends of the severity of issus being raised
Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assume 0 critical
Serious | 5 | 5 | 6 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
High | 28 | 32 | 35 | 38 | 43 | 45 | 46 | 47 | 47 | 48 | 50 | 50 | 51 | 52 | 52 | 52 | 52
Medium | 15 | 21 | 24 | 29 | 37 | 39 | 39 | 41 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44
Low | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Very Low | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Total Issues Resolved By Severity | 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24thApr | 1st May | * update each week so we can the trends of the severity of issus being raised
Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Assume 0 critical
Serious | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
High | 11 | 15 | 25 | 28 | 32 | 35 | 36 | 37 | 40 | 42 | 43 | 43 | 43 | 44 | 44 | 44 | 44
Medium | 11 | 12 | 12 | 16 | 21 | 24 | 28 | 30 | 32 | 34 | 36 | 37 | 39 | 41 | 41 | 41 | 41
Low | 19 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Very Low | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18
Total Issues Outstanding By Type | 10th Jan | 17th Jan | 24th Jan | 31st Jan | 7th Feb | 14th Feb | 21st Feb | 28th Feb | 6th Mar | 13th Mar | 20th Mar | 27th Mar | 3rd Apr | 10th Apr | 17th Apr | 24thApr | 1st May | * update each week so we can how we are doing against each severity level
Critical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Serious | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
High | 17 | 17 | 10 | 10 | 11 | 10 | 10 | 10 | 7 | 6 | 7 | 7 | 8 | 8
Medium | 4 | 9 | 12 | 13 | 16 | 15 | 11 | 11 | 12 | 10 | 8 | 7 | 5 | 3
Low | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Very Low | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2

## Instructions
Use this spreadsheet to track and forecast incidents/problems. This is particularly useful when you are in ST, UAT or Warranty phase where daily tracking may be necessary
To be used for prodcutivity planning, warranty forecast etc in a Production Support scenario
Presented illustration assumes the following dates ( the numbers are random and do not relate to any actual implementation)
Starting balance positions as W/E 10th Feb, data complete date as of W/E of 10th Apr, Expected project end date of W/E 1st May
For each completed week you should make forcast same as actual, review the gap and adjust forecast, expected date accordingly for future weeks
The daily tracker, which enables you to enter Raised and Resolved info, should be updated daily and the weekly tracker should be reviwed