## Summary
W/E date | 2020-02-14
Project status | Green
Phase | Code and UT
Planned Phase End | 2020-03-13
Planned Project End | 2020-03-13
Summary of Risks |  |  |  |  | Summary of Issues
Count of Status | Column Labels |  |  |  | Count of Serial # | Column Labels
Row Labels | Open | Closed | Grand Total |  | Row Labels | Open | Closed | Grand Total
High | 1 |  | 1 |  | High | 1 |  | 1
Medium | 1 |  | 1 |  | Medium |  | 1 | 1
Low |  | 1 | 1 |  | Grand Total | 1 | 1 | 2
Grand Total | 2 | 1 | 3
Summary of Milestones |  |  |  |  | Summary of Dependencies
Row Labels | Count of Status |  | Row Labels | Count of Status | Row Labels | Count of Status
Red | 1 |  | Closed | 1 | Open | 2
Amber | 1 |  | In Progress | 4 | (blank)
Green | 6 |  | Not started | 4 | Grand Total | 2
Completed | 1 |  | Grand Total | 9
Grand Total | 9
Summary of Assumptions |  |  |  |  | Summary of Actions
Row Labels | Count of Status |  |  |  | Row Labels | Count of Status
Not validated | 1 |  |  |  | Closed | 2
Validated | 1 |  |  |  | Open | 4
Grand Total | 2 |  |  |  | (blank)
[5 empty] | Grand Total | 6
Summary of Changes
Row Labels | Count of Status | Sum of Estimated cost($)
Accepted | 1 | 100000
100000 | 1 | 100000
Pending | 1 | 125000
125000 | 1 | 125000
Rejected | 1 | 50000
50000 | 1 | 50000
Grand Total | 3 | 275000

## Milestones
Serial # | Phase | Description | Workstream | Owner | Planned start | Actual start | Planned end | Actual end | Status | RAG Status | Comments
AS01 | Business Requirements |  |  | John Doe |  |  |  |  | Closed | Completed
AS02 | Technical Requirements |  |  | John Doe |  |  |  |  | In Progress | Red
AS03 | HLD |  |  | John Doe |  |  |  |  | In Progress | Amber
AS04 | LLD |  |  | John Doe |  |  |  |  | In Progress | Green
AS05 | Code and UT |  |  | John Doe |  |  |  |  | In Progress | Green
AS06 | ST |  |  | John Doe |  |  |  |  | Not started | Green
AS07 | UAT |  |  | John Doe |  |  |  |  | Not started | Green
AS08 | Implementation |  |  | John Doe |  |  |  |  | Not started | Green
AS09 | Warranty |  |  | John Doe |  |  |  |  | Not started | Green

## Risks
Serial # | Title | Description | Impact | Probability rating | Impact rating | Risk score | Risk rating | $value (if applicable) | Response | Date Opened | Date Reviewed | Progress update | Status | Owner | Date closed
R01 |  |  |  | 3 | 3 | 9 | High | 100000 | Reduce | 2020-01-13 | 2020-03-31 |  | Open | John Doe
R02 |  |  |  | 3 | 2 | 6 | Medium |  | Reduce | 2020-01-17 | 2020-03-31 |  | Open | John Doe
R03 |  |  |  | 2 | 1 | 2 | Low |  | Avoid | 2020-01-13 | 2020-03-31 |  | Closed | John Doe

## Risk Matrix
Use this information to populate the Risk worksheet
Risk Probability | Description | Risk Impact | Description
1 | Unlikely | 1 | Little impact
2 | Somewhat likely | 2 | Considerable impact
3 | Likely | 3 | Very high impact
4 | Imminent | 4 | Critical impact
Risk score matrix |  | Risk Response Categories
< 4 | Low | Accept | Accept the risk, do nothing
4 to 8 | Medium | Reduce | Mitigate by taking appropriate action
9 to 15 | High | Transfer | Transfer to 3rd party e.g. by outsourcing
16 | Critical | Avoid | Avoid the risk completely (e.g. do everything onsite to avoid risks with offshoring)
$Value | Applicable if there is a direct commercial impact of the risk e.g. extra cost of continuing an existing supporting arrangement because replacement not ready or delay in delivery means testing team sitting idle for 3 extra weeks burning XXX extra

## Issues
Serial # | Title | Description | Impact | Severity | Owner | Date Opened | Date Reviewed | Progress update | Status | Date closed
I01 | Single point of failure |  | Creating a bottleneck in resolving issues | High | John Doe | 2020-01-13 | 2020-03-31 |  | Open
I02 | Not enough support from another team |  | Prodcutivity reduced | Medium | Jon Doe |  |  |  | Closed

## Dependencies
Serial # | Title | Description | Date Opened | Comments | Status | Date closed
D01 |  |  |  |  | Open
D02 |  |  |  |  | Open

## Assumptions
Serial # | Title | Description | Date Opened | Comments | Status | Date validated
A01 |  |  |  |  | Validated
A02 |  |  |  |  | Not validated

## Actions
Serial # | Description | Workstream | Owner | Opened date | Target date | Progress update | Status
A01 | [6 empty] | Open
A02 | [6 empty] | Open
A03 | [6 empty] | Closed
A04 | [6 empty] | Closed
A05 | [6 empty] | Open
A06 | [6 empty] | Open

## Financials
Phase/Task Description | Agreed Budget | Current Spend to Date | Forecast Spend to Complete | Variance From Budget | Total Cost | Comments
System upgrade | 135000 | 90000 | 50000 | 5000 | 140000 | Fixed price
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
Current Total | 135000 | 90000 | 50000 | 5000 | 140000
Expenses (Actual expenses to above date. Note that expenses remain as estimates until the month-end)
| Agreed Budget | Current Spend to Date | Forecast Spend to Complete | Variance from Budget | Total Cost
Requirement hothouse | 500 | 450 | 100 | 50 | 550
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0
Total Expenses | 500 | 450 | 100 | 50 | 550
Invoicing
Milestone or Monthly T&M Trigger | Invoice Date | Invoice Amount | Payment Date | Paid Amount | Invoice No. |  | PO No.
Invoice Total |  | 0 | Total Paid | 0
Note on A2: Author: Include CR's

## Decisions
Serial # | Description | Date | Forum | Agreed Yes/No | Comments
D01 |  |  |  | Yes
D02 |  |  |  | No

## Change Register
Serial # | Description | Date raised | Forum | Status | Comments | Doc location/link | Estimated cost($)
C01 |  |  |  | Accepted |  |  | 100000
C02 |  |  |  | Rejected |  |  | 50000
C03 |  |  |  | Pending |  |  | 125000

## Artifacts
Serial # | Document name | Author | Owner | Location | Comments
1 | Project Initiation Document (PID)
2 | Statement of Work (SOW)
3 | Project Log
4 | Business Requirements
5 | Non Functional Requirements
6 | High Level Design docs
7 | Detailed Design Docs
8 | Supporting documents
9 | Configuration Management Strategy and plan
10 | Communications Stratefy and plan
11 | Test Strategy
12 | Test Plan
13 | High Level Test Scenarios
14 | Test Completion Report
15 | Acceptance criteria
16 | Implementation Plan and SOE
17 | Warranty/handover to BAU Plan
18 | Warranty burndown chart